## Project Plan
Project Name | Test Paper Generator |  |  |  | Project Mentor | Madhur Nagar
Project Deliverable
Scope Statement
Start Date | 2023-09-28 | End Date | 2023-10-20 |  | Overall Progress
Task Name | Assigned To | Start Date | End Date | Duration (days) | Status | Comments
Class Diagram | Ananya R Siri | 2023-09-28 | 2023-09-29 | 2 | Completed | N/A
Questioners | mahalaxminagula2@gmail.com | 2023-09-28 | 2023-10-20 | 2 | In progress | N/A
Functionalities | Kavya S 1EP19IS045 | 2023-09-28 | 2023-09-29 | 2 | Completed | N/A
Usr Case Diagram | Yamini Agiwal | 2023-09-28 | 2023-09-29 | 2 | Completed | N/A
GIT HUB Set Up | Ananya R Siri Kavya S 1EP19IS045 mahalaxminagula2@gmail.com Yamini Agiwal | 2023-09-29 | 2023-09-29 | 1 | Completed | N/A
Data Base Set UP | Ananya R Siri Kavya S 1EP19IS045 mahalaxminagula2@gmail.com Yamini Agiwal | 2023-09-29 | 2023-09-29 | 1 | Completed | N/A
Task 7
Task 8
Task 9
Task 10
Task 11
Task 12
Task 13
Task 14
Task 15

## BRD
Project Name
Project Mentor
Date
Executive Summary
Project Objectives
Project Scope

## Project Timeline
Tasks | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20
Create Project Documentation
Create UML Diagrams
Create Git repository
Create Database
Create REST APIs
Create Responsive Frontend Modules
Integrate APIs
Unit Testing
Functional testing
Deploy
Create Presentation