## Project Plan
Project Name | Test Paper Generator |  |  |  | Project Mentor | Madhur Nagar
Project Deliverable
Scope Statement
Start Date | 2023-09-28 | End Date | 2023-10-20 |  | Overall Progress
Task Name | Assigned To | Start Date | End Date | Duration (days) | Status | Comments
Class Diagram | Ananya R Siri | 2023-09-28 | 2023-09-29 | 2 | Completed | N/A
Questioners | mahalaxminagula2@gmail.com | 2023-09-28 | 2023-10-20 | 2 | In progress | N/A
Functionalities | Kavya S 1EP19IS045 | 2023-09-28 | 2023-09-29 | 2 | Completed | N/A
Use Case Diagram | Yamini Agiwal | 2023-09-29 | 2023-09-29 | 1 | Completed | N/A
Git Hub Set Up | Ananya R Siri Kavya S 1EP19IS045 mahalaxminagula2@gmail.com Yamini Agiwal | 2023-09-29 | 2023-09-29 | 1 | Completed | N/A
Data Base Set UP | Ananya R Siri Kavya S 1EP19IS045 mahalaxminagula2@gmail.com Yamini Agiwal | 2023-09-29 | 2023-09-29 | 1 | Completed | N/A
Data Base Structure | Kavya S 1EP19IS045 Yamini Agiwal | 2023-10-03 | 2023-10-03 | 1 | Completed | N/A
ER Diagram | Ananya R Siri mahalaxminagula2@gmail.com | 2023-10-03 | 2023-10-03 | 1 | Completed | N/A
Admin jwt | mahalaxminagula2@gmail.com | 2023-10-04 | 2023-10-04 | 1 | in progress | N/A
Adding Subject and Question | Ananya R Siri | 2023-10-04 | 2023-10-04 | 1 | in progress | N/A
Task 11
Task 12
Task 13
Task 14
Task 15

## Sheet4
| test 1 |  |  | test 2
| client 1 |  |  | client 2
section 1 | 1 |  | section 1 | 3
subject | java | sub 1 | subject | java | sub 1
level | e m d |  | level | m d
number of question | 5_10_2 |  | number of question | 5_10_4
section 2 | 2 |  | section 2 | 4
subject | oops | sub 2 | subject | oops | sub 2
level | m d |  | level | e m
number of question | 5_10_5 |  | number of question | 5_8_2

## BRD
Project Name | TEST PAPER GENERATOR
Project Mentor | Madhur Nagar
Date | 2023-09-28
Executive Summary
Project Objectives
Project Scope

## Project Timeline
Tasks | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20
Create Project Documentation
Create UML Diagrams
Create Git repository
Create Database
Create REST APIs
Create Responsive Frontend Modules
Integrate APIs
Unit Testing
Functional testing
Deploy
Create Presentation